PROJECT PLAN

EHR System Implementation Training Program

Prepared for

Meridian Health Partners

Prepared by

Zach Dornisch, M.S. IDT

Learning & Development

March 2026

Version 1.0

# Document History

| Date | Version | Changes | Author | Approved By |
| --- | --- | --- | --- | --- |
| 03/01/2026 | 1.0 | Initial Draft | Z. Dornisch |  |
| 03/15/2026 | 1.1 | Incorporated stakeholder feedback | Z. Dornisch |  |

# Project Resources

| Role | Name |
| --- | --- |
| Project Sponsor | Dr. Sarah Chen, Chief Medical Officer |
| Instructional Designer | Zach Dornisch, M.S. IDT |
| Subject Matter Expert (IT) | James Whitfield, IT Director |
| Subject Matter Expert (Clinical) | Dr. Maria Santos, Clinical Lead |
| Project Manager | Lisa Park, Operations Manager |
| Change Management Lead | Rachel Kim, HR Director |

# 1. Project Overview

This project plan governs the design, development, and implementation of the MeridianChart EHR training program for Meridian Health Partners. The program will prepare 339 employees across five role groups for the system go-live in September 2026, ensuring all staff can confidently use the new system and maintain clinical workflows with minimal disruption.

| Item | Detail |
| --- | --- |
| Project Name | MeridianChart EHR Training Program |
| Project Sponsor | Dr. Sarah Chen, Chief Medical Officer |
| Project Manager | Lisa Park, Operations Manager |
| Instructional Designer | Zach Dornisch, M.S. IDT |
| Start Date | March 1, 2026 |
| Target Completion | September 30, 2026 |
| Methodology | Successive Approximation Model (SAM) |
| Total Budget | $5,649 (detailed breakdown in Section 5) |

# 2. Scope

## 2.1 In Scope

- Comprehensive learning needs analysis identifying performance gaps for all five role groups.

- Instructional design document with blended learning strategy, content structure, and assessment plan.

- Storyboard development for all five training modules (estimated 40–50 lessons total).

- Development of five role-specific eLearning modules using Articulate Storyline 360 (SCORM 1.2 compliant).

- Instructor-led practice session design with facilitator guides and sandbox scenario scripts.

- Job aids and quick reference guides for all role groups (printed and digital).

- LMS configuration and content deployment on HealthLearn platform.

- Pilot training delivery at two clinic locations with feedback collection and content refinement.

- Full rollout training delivery across all 12 clinic locations.

- Post-training evaluation at 30, 60, and 90 days using Kirkpatrick Four-Level Model.

## 2.2 Out of Scope

- MeridianChart system configuration and technical implementation (managed by IT under separate EHR Project).

- Vendor certification training for IT Support and system administrators (managed directly by MeridianChart vendor).

- Organizational change management communications (managed by HR and Operations with L&D consultation/coordination).

- System hardware procurement, network upgrades, and infrastructure preparation.

# 3. Milestones and Timeline

| # | Milestone | Target Date | Owner | Status |
| --- | --- | --- | --- | --- |
| 1 | Needs Analysis Complete & Approved | Apr 15, 2026 | Z. Dornisch | Complete |
| 2 | Design Document Approved | May 1, 2026 | Z. Dornisch | Complete |
| 3 | All Storyboards Complete & SME-Reviewed | May 31, 2026 | Z. Dornisch | In Progress |
| 4 | Alpha Build – Modules 1 & 2 (Dev + QA) | Jun 15, 2026 | Z. Dornisch | Not Started |
| 5 | Beta Build – Modules 3, 4, 5 (Dev + QA) | Jul 1, 2026 | Z. Dornisch | Not Started |
| 6 | Full SME & Stakeholder Review | Jul 15, 2026 | J. Whitfield | Not Started |
| 7 | Pilot Training (2 Clinics) | Aug 1–15, 2026 | Z. Dornisch | Not Started |
| 8 | Pilot Feedback Incorporated | Aug 22, 2026 | Z. Dornisch | Not Started |
| 9 | Full Rollout Training Begins | Aug 25, 2026 | L. Park | Not Started |
| 10 | System Go-Live & Live Support | Sep 1, 2026 | All | Not Started |
| 11 | 30/60/90-Day Evaluations Complete | Dec 2026 | Z. Dornisch | Not Started |

Milestones 1–3 are dependent on completion in sequence. Milestones 4–5 run in parallel (alpha and beta tracks). Milestone 6 (SME review) is dependent on Milestone 5 completion. Milestone 7 is dependent on Milestone 6 approval. Milestone 10 is a hard deadline driven by vendor and organizational commitments.

# 4. Resource Allocation

| Resource | Role | Allocation | Duration |
| --- | --- | --- | --- |
| Zach Dornisch | Instructional Designer (Lead) | 100% FTE | Mar–Sep 2026 (7 months) |
| James Whitfield | SME (IT Director) | 4 hrs/week | Apr–Aug 2026 |
| Dr. Maria Santos | SME (Clinical Lead) | 4 hrs/week | Apr–Aug 2026 |
| Lisa Park | Project Manager | 8 hrs/week | Mar–Sep 2026 |
| Peer Champions (6) | Training Support | 2 hrs/week per champion | Aug–Oct 2026 |
| Rachel Kim | Change Management Lead | 2 hrs/week | Apr–Sep 2026 |

# 5. Budget Summary

| Line Item | Cost | Status |
| --- | --- | --- |
| Articulate Storyline 360 (annual license) | $1,399 | Approved |
| Adobe Creative Cloud (design; 6 months @ $600/year prorated) | $300 | Approved |
| Vyond (animated video; 3 months @ $400/month) | $1,200 | Approved |
| Camtasia (screen recording/editing; perpetual license) | $299 | Approved |
| Stock photography/media (authentic healthcare imagery) | $400 | Approved |
| LMS configuration (HealthLearn) | Included (existing) | N/A |
| Sandbox environment access (MeridianChart vendor) | Included in vendor contract | Pending vendor |
| Printed job aids (500 copies, color, 2-page) | $750 | Approved |
| Peer champion stipends ($500 × 6 champions) | $3,000 | Approved |
| TOTAL ESTIMATED BUDGET | $5,649 |  |

Budget excludes labor costs for Z. Dornisch and other staff (covered by departmental budgets). This represents software, media, and operational expenses only. Contingency: 10% buffer (~$565) available for unexpected expenses.

# 6. Communication Plan

| Audience | Communication | Frequency | Channel | Owner |
| --- | --- | --- | --- | --- |
| Project Sponsor (Dr. Chen) | Executive status update | Bi-weekly | Email + 30-min meeting | L. Park |
| SMEs (J. Whitfield, M. Santos) | Content review requests | As needed (avg 2/week) | Email + Teams + in-person | Z. Dornisch |
| Department leads / managers | Training schedule & logistics | Monthly | Email newsletter | L. Park |
| All staff (339) | Program announcements, key milestones | Milestone-driven | Email + intranet + posters | HR + L&D |
| Pilot participants (40 staff) | Pilot logistics, feedback sessions | Weekly during pilot | Email + in-person debrief | Z. Dornisch |

# 7. Risk Management

| Risk | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| SME availability / competing priorities | High | High | Schedule reviews 2 weeks in advance; identify backup SMEs from each department; establish review SLA (3 business days) |
| Sandbox environment delays from vendor | Medium | High | Request access 4 weeks in advance; begin conceptual (non-sandbox) training first; escalate to vendor PM if slip beyond Jun 1 |
| Staff resistance to new system | High | Medium | Deploy change champion program; secure visible leadership support (CEO email); communicate benefits early; build flexibility into training |
| Scope creep / additional modules requested | Medium | Medium | Establish formal change request process; document scope in this plan; evaluate requests vs. Sep 1 deadline; defer non-critical additions |
| Content inaccuracy / MeridianChart workflow changes | Low | High | Three-stage review process (SME + stakeholder + QA); iterative SAM cycles; flag for updates if vendor releases changes Jun-Aug |

# 8. Quality Assurance

- All eLearning modules will undergo three review cycles: SME content review, stakeholder UX review, and QA technical testing.

- QA checklist includes: content accuracy vs. MeridianChart user guide, functionality testing (all interactions work), SCORM 1.2 compliance, accessibility (WCAG 2.1 AA with NVDA/JAWS testing), browser compatibility (Chrome, Edge, Safari latest versions), and mobile responsiveness.

- Pilot training at two clinic locations serves as final validation; feedback incorporated before full rollout.

- Acceptance criteria: ≥94% assessment pass rate; ≥4.0/5.0 learner satisfaction; 90% attendance at ILT sessions.

# Stakeholder Sign-Off

By signing below, stakeholders confirm they have reviewed this Project Plan and approve the scope, timeline, resources, and approach.

| Name | Title | Signature | Date |
| --- | --- | --- | --- |
| Dr. Sarah Chen | Chief Medical Officer |  |  |
| James Whitfield | IT Director |  |  |
| Lisa Park | Operations Manager |  |  |